## Summary
Jorgeasaurus Feature Status | Jorgeasaurus Feature Status | Jorgeasaurus Feature Status | Jorgeasaurus Feature Status | Jorgeasaurus Feature Status | Jorgeasaurus Feature Status
Canonical tracker for feature stories, expected behavior, testing status, errors, fixes, and retest state. | Canonical tracker for feature stories, expected behavior, testing status, errors, fixes, and retest state. | Canonical tracker for feature stories, expected behavior, testing status, errors, fixes, and retest state. | Canonical tracker for feature stories, expected behavior, testing status, errors, fixes, and retest state. | Canonical tracker for feature stories, expected behavior, testing status, errors, fixes, and retest state. | Canonical tracker for feature stories, expected behavior, testing status, errors, fixes, and retest state.
Metric | Value |  | Area | Stories
Total user stories | 40 |  | About | 1
Ready for Test | 0 |  | Accessibility | 1
Testing | 0 |  | Analytics | 1
Tested | 0 |  | Blog Posts | 8
Error Found | 0 |  | Build | 1
Fixed | 0 |  | Content Integrity | 1
Retest Passed | 40 |  | Data Formatting | 1
Won't Fix | 0 |  | Homepage | 5
|  |  | Images | 3
|  |  | Navigation | 2
Source Data | Count |  | Projects | 3
Published posts | 26 |  | Responsive UX | 1
Unique post tags | 43 |  | Routing | 4
Posts with social images | 6 |  | SEO | 5
Live project cards | 6 |  | Social Card | 1
Repo/experiment cards | 14 |  | Visual Shell | 2
Total project cards | 20
User stories documented | 40
Issues documented | 1
Open issues | 0

## User Stories
User Stories and Test Status | User Stories and Test Status | User Stories and Test Status | User Stories and Test Status | User Stories and Test Status | User Stories and Test Status | User Stories and Test Status | User Stories and Test Status | User Stories and Test Status | User Stories and Test Status | User Stories and Test Status | User Stories and Test Status | User Stories and Test Status | User Stories and Test Status | User Stories and Test Status
Update this sheet during the testing loop. One row equals one user behavior or testable feature contract derived from the current code. | Update this sheet during the testing loop. One row equals one user behavior or testable feature contract derived from the current code. | Update this sheet during the testing loop. One row equals one user behavior or testable feature contract derived from the current code. | Update this sheet during the testing loop. One row equals one user behavior or testable feature contract derived from the current code. | Update this sheet during the testing loop. One row equals one user behavior or testable feature contract derived from the current code. | Update this sheet during the testing loop. One row equals one user behavior or testable feature contract derived from the current code. | Update this sheet during the testing loop. One row equals one user behavior or testable feature contract derived from the current code. | Update this sheet during the testing loop. One row equals one user behavior or testable feature contract derived from the current code. | Update this sheet during the testing loop. One row equals one user behavior or testable feature contract derived from the current code. | Update this sheet during the testing loop. One row equals one user behavior or testable feature contract derived from the current code. | Update this sheet during the testing loop. One row equals one user behavior or testable feature contract derived from the current code. | Update this sheet during the testing loop. One row equals one user behavior or testable feature contract derived from the current code. | Update this sheet during the testing loop. One row equals one user behavior or testable feature contract derived from the current code. | Update this sheet during the testing loop. One row equals one user behavior or testable feature contract derived from the current code. | Update this sheet during the testing loop. One row equals one user behavior or testable feature contract derived from the current code.
Story ID | Area | Feature | User Story | Expected Behavior | Source Evidence | Priority | Story Status | Initial Test Status | Error Summary | Fix Status | Retest Status | Last Verified | Test Notes | Automation Candidate
US-001 | Routing | Root homepage route | As a reader, I want `/` to load the blog homepage so I can discover the site and latest posts. | The root route renders the hero, topbar, wallpaper, recent posts heading, first page of posts, and document title `Jorgeasaurus`. | src/App.tsx; src/pages/Home.tsx | P0 | Retest Passed | Pass |  | Not Needed Yet | Pass | 2026-06-28 23:20 | Homepage route rendered hero, topbar, wallpaper, and five post cards. Post-fix retest pass. | Playwright route render
US-002 | Routing | Canonical post routes | As a reader, I want published posts to open from clean slug URLs and `/post/:slug` URLs. | Both `/:slug` and `/post/:slug` render the same post template for valid metadata slugs and show the same title/content. | src/App.tsx; src/pages/Post.tsx; src/content/posts.ts | P0 | Retest Passed | Pass |  | Not Needed Yet | Pass | 2026-06-28 23:20 | Clean and /post routes rendered make-yourself-obsolete. Post-fix retest pass. | Playwright data-driven route test
US-003 | Routing | Legacy untitled redirect | As a returning visitor with an old `/untitled` link, I want to be redirected to the intended post. | `/untitled` redirects with replace navigation to `/intune-device-queries-to-level-up-your-device-management`. | src/App.tsx | P1 | Retest Passed | Pass |  | Not Needed Yet | Pass | 2026-06-28 23:20 | /untitled redirected to the expected post slug. Post-fix retest pass. | Playwright navigation assertion
US-004 | Routing | Unknown page handling | As a visitor on a bad URL, I want a clear not-found page and a way back home. | Unknown unmatched routes render Page Not Found, set document title to `Page Not Found ¦ Jorgeasaurus`, set robots to `noindex,nofollow`, and provide a Back to home link. | src/App.tsx; src/pages/NotFound.tsx | P0 | Retest Passed | Pass |  | Not Needed Yet | Pass | 2026-06-28 23:20 | Unmatched multi-segment route rendered NotFound with noindex and home link. Post-fix retest pass. | Playwright route/meta test
US-005 | Navigation | Primary topbar navigation | As a visitor, I want consistent navigation across site pages. | Topbar appears on blog pages, brand link returns home, Home/Projects/About links route internally, and the active nav item reflects the current pathname. | src/components/Topbar.tsx | P0 | Retest Passed | Pass |  | Not Needed Yet | Pass | 2026-06-28 23:20 | Topbar rendered across primary pages with expected active states. Post-fix retest pass. | Playwright navigation test
US-006 | Navigation | Topbar social links | As a visitor, I want quick access to GitHub and LinkedIn profiles. | GitHub and LinkedIn icon links open the configured external URLs in a new tab with `rel="noopener noreferrer"` and accessible labels. | src/components/Topbar.tsx; src/components/SocialIcon.tsx | P1 | Retest Passed | Pass |  | Not Needed Yet | Pass | 2026-06-28 23:20 | Topbar social links had accessible labels, target, and rel attributes. Post-fix retest pass. | DOM attribute test
US-007 | Homepage | Hero profile block | As a first-time visitor, I want to understand who the site is for and where to find profile links. | Homepage hero shows `> Jorgeasaurus`, `Learn. Build. Automate.`, field-note copy, GitHub link, and Microsoft MVP link with icons. | src/pages/Home.tsx | P0 | Retest Passed | Pass |  | Not Needed Yet | Pass | 2026-06-28 23:20 | Hero brand, tagline, copy, and profile links rendered. Post-fix retest pass. | Playwright text/link assertions
US-008 | Homepage | Post sorting and latest card | As a reader, I want the newest posts first so current content is easy to find. | Posts are sorted descending by date; page 1 shows five posts; the newest unfiltered post is visually featured and marked Latest. | src/pages/Home.tsx; src/lib/posts.ts; src/components/PostCard.tsx | P0 | Retest Passed | Pass |  | Not Needed Yet | Pass | 2026-06-28 23:20 | Posts sorted newest first and latest card is featured. Post-fix retest pass. | Data-driven DOM order test
US-009 | Homepage | Pagination | As a reader, I want to browse older posts without loading every article at once. | Pagination appears when filtered results exceed five posts, page links preserve active tag filters, disabled Newer/Older states render at boundaries, and invalid page values clamp to a valid page. | src/pages/Home.tsx | P0 | Retest Passed | Pass |  | Not Needed Yet | Pass | 2026-06-28 23:20 | Pagination, tag preservation, and page clamping passed. Post-fix retest pass. | Playwright query-param test
US-010 | Homepage | Tag filtering | As a reader, I want to click a tag and see only matching posts. | Post-card tag links set `?tag=<encoded tag>`, the heading changes to `Tagged: <tag>`, visible posts all include the tag, and Clear filter returns to `/`. | src/pages/Home.tsx; src/components/PostCard.tsx; src/content/posts.ts | P0 | Retest Passed | Pass |  | Not Needed Yet | Pass | 2026-06-28 23:20 | Tag chip filtered posts and exposed clear filter link. Post-fix retest pass. | Playwright tag-link test
US-011 | Homepage | Empty tag state | As a reader who lands on a tag URL with no matches, I want a clear empty state. | A non-matching tag query shows `No posts tagged ...`, keeps the clear-filter link visible, and does not render stale post cards. | src/pages/Home.tsx | P1 | Retest Passed | Pass |  | Not Needed Yet | Pass | 2026-06-28 23:20 | Empty tag query rendered empty state without stale cards. Post-fix retest pass. | Playwright query-param test
US-012 | SEO | Filtered homepage robots meta | As the site owner, I want filtered and paginated list URLs excluded from indexing while the main homepage remains indexable. | Homepage sets robots to `index,follow` only on unfiltered page 1; tag filters or page > 1 set `noindex,follow`; unmount restores the previous meta value. | src/pages/Home.tsx | P1 | Retest Passed | Pass |  | Not Needed Yet | Pass | 2026-06-28 23:20 | Homepage robots meta switched correctly for base, tag, and paginated states. Post-fix retest pass. | Playwright meta assertion
US-013 | Blog Posts | Post-card navigation | As a reader, I want each post card to behave like a clear article link. | Card title link covers the card, opens the clean slug route, tag chips remain separately clickable, and the visible CTA arrow is decorative. | src/components/PostCard.tsx | P0 | Retest Passed | Pass |  | Not Needed Yet | Pass | 2026-06-28 23:20 | Post card title and tag links had expected destinations. Post-fix retest pass. | Playwright click target test
US-014 | Blog Posts | Dynamic MDX article loading | As a reader, I want each published article to load its MDX content from the metadata slug. | Valid slugs load the matching MDX component, show the post date/title/description, and set document title to `<post title> ¦ Jorgeasaurus`. | src/pages/Post.tsx; src/content/*.mdx; src/content/posts.ts | P0 | Retest Passed | Pass |  | Not Needed Yet | Pass | 2026-06-28 23:20 | All 26 published post slugs rendered their title and document title. Post-fix retest pass. | Data-driven Playwright post crawl
US-015 | Blog Posts | Post loading state | As a reader on a slow connection, I want feedback while article content loads. | The post route renders a glass loading panel with spinner and `Loading...` while MDX import is pending. | src/pages/Post.tsx | P2 | Retest Passed | Pass |  | Not Needed Yet | Pass | 2026-06-28 23:20 | Delayed dynamic import exposed the loading panel. Post-fix retest pass. | Component or route-level async test
US-016 | Blog Posts | Missing post state | As a visitor on an invalid post slug, I want a clear article-level error. | A slug that matches no metadata or no MDX module renders `Post Not Found` with explanatory copy instead of crashing. | src/pages/Post.tsx | P0 | Retest Passed | Pass |  | Not Needed Yet | Pass | 2026-06-28 23:20 | Invalid single-slug post route rendered article-level not-found state. Post-fix retest pass. | Playwright invalid slug test
US-017 | Blog Posts | Article reading progress | As a reader, I want a subtle progress indicator while scrolling long posts. | A fixed reading-progress bar scales from 0 to 1 based on document scroll position and updates on scroll/resize. | src/pages/Post.tsx; src/styles/App.css | P1 | Retest Passed | Pass |  | Not Needed Yet | Pass | 2026-06-28 23:20 | Reading progress transform changed after scrolling a long post. Post-fix retest pass. | Playwright scroll style test
US-018 | Blog Posts | Adjacent article navigation | As a reader finishing a post, I want to move to newer or older field notes. | Post footer shows newer and/or older links based on sorted post order; boundary posts reserve layout without linking to nonexistent posts. | src/pages/Post.tsx; src/lib/posts.ts | P1 | Retest Passed | Pass |  | Not Needed Yet | Pass | 2026-06-28 23:20 | Adjacent navigation respected newest and oldest boundaries. Post-fix retest pass. | Data-driven boundary test
US-019 | Images | Article hero image | As a reader, I want posts with one configured image to show it prominently. | When a post has exactly one configured image, it appears as an eager-loaded hero figure with alt text, optional caption, and expandable button. | src/pages/Post.tsx; src/content/postImages.ts | P1 | Retest Passed | Pass |  | Not Needed Yet | Pass | 2026-06-28 23:20 | Post with one configured image rendered an expandable hero image. Post-fix retest pass. | Data-driven image render test
US-020 | Images | Inline MDX image expansion | As a reader, I want article images to be inspectable at a larger size. | MDX `img` elements are wrapped in buttons that open the lightbox when image source exists; images without expansion context still render as normal images. | src/pages/Post.tsx; src/content/*.mdx | P1 | Retest Passed | Pass |  | Not Needed Yet | Pass | 2026-06-28 23:20 | Inline MDX images were wrapped in expandable trigger buttons. Post-fix retest pass. | Playwright image click test
US-021 | Images | Image lightbox | As a reader viewing an expanded image, I want obvious ways to close it. | Lightbox uses native dialog, prevents body scroll while open, closes through close button, backdrop click, or cancel/escape, and restores body overflow on close. | src/pages/Post.tsx | P1 | Retest Passed | Pass |  | Not Needed Yet | Pass | 2026-06-28 23:20 | Lightbox opened and closed with body overflow restoration. Post-fix retest pass. | Playwright dialog interaction test
US-022 | About | About profile page | As a visitor, I want to learn who Jorge Suarez is and how to connect. | `/about` renders the profile copy, portrait image, Microsoft MVP badge link, GitHub/LinkedIn/RSS links, and document title `About ¦ Jorgeasaurus`. | src/pages/About.tsx | P0 | Retest Passed | Pass |  | Not Needed Yet | Pass | 2026-06-28 23:20 | About page rendered profile, imagery, MVP/profile links, and RSS link. Post-fix retest pass. | Playwright route/link/image test
US-023 | Projects | Projects landing hero | As a visitor, I want a clear projects page introduction before project cards. | `/projects` renders the project hero with title `Tools for endpoint work`, endpoint-tooling copy, and document title `Projects ¦ Jorgeasaurus`. | src/pages/Projects.tsx | P0 | Retest Passed | Pass |  | Not Needed Yet | Pass | 2026-06-28 23:20 | Projects hero rendered title, copy, and page title. Post-fix retest pass. | Playwright route render test
US-024 | Projects | Project catalog sections | As a visitor, I want live products separated from repositories and experiments. | Projects page renders 6 featured live project cards and 14 repository/experiment cards under their respective headings. | src/pages/Projects.tsx | P0 | Retest Passed | Pass |  | Not Needed Yet | Pass | 2026-06-28 23:20 | Projects page rendered 6 live projects and 14 repo/experiment cards. Post-fix retest pass. | Playwright card count test
US-025 | Projects | Project-card outbound links | As a visitor, I want project cards to take me to the correct project site or repository. | Each project card shows kind, name, description, tags, and CTA; CTA opens the configured href in a new tab with `noopener noreferrer` and an aria label including the project name. | src/pages/Projects.tsx | P0 | Retest Passed | Pass |  | Not Needed Yet | Pass | 2026-06-28 23:20 | All 20 project cards had expected CTA attributes. Post-fix retest pass. | DOM attribute/data-driven test
US-026 | Social Card | Social-card route | As the site owner, I want a dedicated visual route for generating the default social preview image. | `/social-card` renders the full social-card layout with brand mark and tagline, sets title `Jorgeasaurus Social Card`, and is marked noindex in generated static HTML. | src/pages/SocialCard.tsx; scripts/generate-post-html.mjs | P1 | Retest Passed | Pass |  | Not Needed Yet | Pass | 2026-06-28 23:20 | Social-card route rendered and generated static HTML is noindex. Post-fix retest pass. | Playwright route/static HTML test
US-027 | SEO | RSS feed | As a subscriber, I want an RSS feed for all posts. | `public/rss.xml` is generated from the post catalog, sorted newest first, with title/link/guid/pubDate/description and category elements for tags. | scripts/generate-rss.mjs; public/rss.xml; src/content/posts.ts | P0 | Retest Passed | Pass |  | Not Needed Yet | Pass | 2026-06-28 23:20 | RSS feed contained 26 items and tag categories. Post-fix retest pass. | XML parse/count/order test
US-028 | SEO | Sitemap | As a search crawler, I want a sitemap containing primary pages and published posts. | `public/sitemap.xml` includes root, about, projects, and every post slug with expected changefreq/priority and lastmod derived from post dates. | scripts/generate-sitemap.mjs; public/sitemap.xml; src/content/posts.ts | P0 | Retest Passed | Pass |  | Not Needed Yet | Pass | 2026-06-28 23:20 | Sitemap contained static pages and all 26 post URLs. Post-fix retest pass. | XML parse/count/url test
US-029 | SEO | Static HTML metadata | As the site owner, I want built static pages to have accurate social and canonical metadata. | Build output creates static HTML for every post plus about/projects/social-card/404, applies per-post OpenGraph/Twitter/JSON-LD article metadata, and removes canonical where configured. | scripts/generate-post-html.mjs; index.html | P0 | Retest Passed | Pass |  | Not Needed Yet | Pass | 2026-06-28 23:20 | Generated static HTML contained expected post, about, and 404 metadata. Post-fix retest pass. | Build artifact HTML inspection
US-030 | SEO | Robots file | As a crawler, I want the site robots policy and sitemap location. | `/robots.txt` allows all user agents and points to `https://jorgeasaur.us/sitemap.xml`. | public/robots.txt | P1 | Retest Passed | Pass |  | Not Needed Yet | Pass | 2026-06-28 23:20 | robots.txt exposed allow rule and sitemap URL. Post-fix retest pass. | Static asset assertion
US-031 | Visual Shell | Wallpaper and glass UI | As a visitor, I want the site to keep a cohesive forest/glass visual system. | Wallpaper stage is aria-hidden, fixed behind content, and shared glass surfaces render without blocking pointer interactions or page content. | src/components/WallpaperStage.tsx; src/hooks/useLiquidGlassSurface.ts; src/styles/App.css | P1 | Retest Passed | Pass |  | Not Needed Yet | Pass | 2026-06-28 23:20 | Wallpaper stage was noninteractive and hidden from assistive technology. Post-fix retest pass. | Playwright screenshot/DOM test
US-032 | Visual Shell | Liquid glass lifecycle | As a visitor, I want glass effects to enhance the UI without causing resource leaks. | Glass surfaces only activate when WebGL is supported and intersecting, reset page snapshot on path changes, observe resize, and destroy observers/containers on cleanup. | src/hooks/useLiquidGlassSurface.ts; src/vendor/liquid-glass-js/container.js | P1 | Retest Passed | Pass |  | Not Needed Yet | Pass | 2026-06-28 23:20 | Liquid glass activated 2 surfaces without severe console/WebGL errors. Post-fix retest pass. | Browser console/resource smoke test
US-033 | Responsive UX | Responsive layout | As a mobile or desktop visitor, I want all primary pages to fit the viewport cleanly. | Home, projects, about, post, not-found, and social-card pages avoid horizontal overflow, keep text readable, and preserve reachable navigation at desktop and mobile widths. | src/styles/App.css; src/pages/*.tsx | P0 | Retest Passed | Pass |  | Not Needed Yet | Pass | 2026-06-28 23:20 | Primary routes had no horizontal overflow at desktop and mobile widths. Post-fix retest pass. | Playwright viewport sweep
US-034 | Accessibility | Accessible labels and decorative icons | As a keyboard or screen-reader user, I want controls and links to have usable names. | Primary nav has an aria label, icon-only links have accessible labels, decorative SVGs are aria-hidden, project/tag groups have labels, dialogs and image buttons have explicit labels, and focus-visible styles are present. | src/components/*.tsx; src/pages/*.tsx; src/styles/App.css | P0 | Retest Passed | Pass |  | Not Needed Yet | Pass | 2026-06-28 23:20 | Accessible labels, decorative icon hiding, image labels, and focus-visible CSS were present. Post-fix retest pass. | Playwright accessibility/DOM assertion
US-035 | Data Formatting | Post date formatting | As a reader, I want post dates to be readable and resilient. | YYYY-MM-DD post dates render as localized long dates, sorting uses local date parsing for date-only values, and invalid date strings fall back to the original value. | src/lib/posts.ts | P1 | Retest Passed | Pass |  | Not Needed Yet | Pass | 2026-06-28 23:20 | Date-only metadata formatted in UI and invalid-date fallback exists in helper. Post-fix retest pass. | Unit-level helper test
US-036 | Build | Production build pipeline | As the site owner, I want build commands to generate feeds, sitemap, app assets, and static metadata in one repeatable path. | `npm run build` runs RSS generation, sitemap generation, TypeScript build, Vite build, and post/static HTML generation successfully. | package.json; scripts/*.mjs | P0 | Retest Passed | Pass |  | Not Needed Yet | Pass | 2026-06-28 23:20 | Build artifacts existed after successful npm run build. Post-fix retest pass. | Command verification
US-037 | Analytics | Vercel Analytics mount | As the site owner, I want Vercel Analytics included without changing user navigation. | `Analytics` from `@vercel/analytics/react` is mounted once outside the router and does not block route rendering. | src/App.tsx; package.json | P2 | Retest Passed | Pass |  | Not Needed Yet | Pass | 2026-06-28 23:20 | Vercel Analytics import and mount are present. Post-fix retest pass. | DOM/build smoke test
US-038 | Content Integrity | MDX metadata coverage | As the site owner, I want every MDX content file represented in the published post catalog. | Every `src/content/*.mdx` slug has a matching `src/content/posts.ts` metadata entry, and every metadata slug has a matching MDX file so content is routable, listed, syndicated, and included in the sitemap. | src/content/*.mdx; src/content/posts.ts | P0 | Retest Passed | Pass |  | Not Needed Yet | Pass | 2026-06-28 23:20 | All 26 MDX files matched metadata slugs. Post-fix retest pass. | Source catalog integrity test
US-039 | Blog Posts | Rich MDX article rendering | As a reader, I want long-form MDX content to render headings, lists, links, blockquotes, and syntax-highlighted code cleanly. | Article content renders MDX headings, paragraphs, lists, links, blockquotes, inline code, fenced code blocks, and highlight classes inside the styled `.post-content` region without horizontal page overflow. | src/pages/Post.tsx; src/content/*.mdx; src/styles/App.css | P0 | Retest Passed | Pass |  | Not Needed Yet | Pass | 2026-06-28 23:20 | Rich MDX headings, lists, highlighted code, and article layout rendered cleanly. Post-fix retest pass. | Playwright article content test
US-040 | Blog Posts | Embedded article media | As a reader, I want embedded article video and inline figures to render accessibly and responsively. | The Intune Hydration Kit post renders the video figure with controls, poster, source type, accessible label, caption, and an inline figure image without causing horizontal overflow. | src/content/intune-hydration-kit-has-a-tui-now.mdx; src/styles/App.css | P1 | Retest Passed | Pass |  | Not Needed Yet | Pass | 2026-06-28 23:20 | Embedded video and inline figure rendered with controls, labels, caption, source, and no overflow. Post-fix retest pass. | Playwright media render test

## Issue Log
Issue Log | Issue Log | Issue Log | Issue Log | Issue Log | Issue Log | Issue Log
Errors found during the user-story testing loop and their fix/retest status. | Errors found during the user-story testing loop and their fix/retest status. | Errors found during the user-story testing loop and their fix/retest status. | Errors found during the user-story testing loop and their fix/retest status. | Errors found during the user-story testing loop and their fix/retest status. | Errors found during the user-story testing loop and their fix/retest status. | Errors found during the user-story testing loop and their fix/retest status.
Issue ID | Story ID | Status | Severity | Error / Observation | Fix Applied | Verification
ISS-001 | US-038 | Fixed | P0 | `src/content/hello-world.mdx` existed without a matching `src/content/posts.ts` metadata entry, so the content was unreachable from the homepage list, direct post route, RSS, sitemap, and generated static HTML. | Added the existing Hello, World post metadata to `src/content/posts.ts` without rewriting the MDX content. | Post-fix 40-story Playwright retest passed; `hello-world` appears in generated RSS, sitemap, static HTML, and the Post Catalog sheet.

## Source Inventory
Source Inventory | Source Inventory | Source Inventory | Source Inventory | Source Inventory
Counts and routes gathered from the current codebase to anchor the user stories. | Counts and routes gathered from the current codebase to anchor the user stories. | Counts and routes gathered from the current codebase to anchor the user stories. | Counts and routes gathered from the current codebase to anchor the user stories. | Counts and routes gathered from the current codebase to anchor the user stories.
Type | Name | Expected Behavior | Source | Status
Route | / | Homepage route renders Home page. | src/App.tsx | Tracked
Route | /projects | Projects route renders Projects page. | src/App.tsx | Tracked
Route | /about | About route renders profile page. | src/App.tsx | Tracked
Route | /social-card | Social-card route renders preview page. | src/App.tsx | Tracked
Route | /post/:slug | Post route renders MDX post by slug. | src/App.tsx | Tracked
Route | /:slug | Clean slug route renders MDX post by slug. | src/App.tsx | Tracked
Route | /untitled | Legacy route redirects to the Intune device queries post. | src/App.tsx | Tracked
Route | * | Unknown routes render NotFound. | src/App.tsx | Tracked
Data | Posts | 26 published post metadata records. | src/content/posts.ts | Tracked
Data | Unique tags | 43 unique tags across posts. | src/content/posts.ts | Tracked
Data | Projects | 20 project cards: 6 live and 14 repo/experiment. | src/pages/Projects.tsx | Tracked
Build artifact | RSS | RSS feed generated from post catalog. | scripts/generate-rss.mjs | Tracked
Build artifact | Sitemap | Sitemap generated from static pages and posts. | scripts/generate-sitemap.mjs | Tracked

## Post Catalog
Post Catalog | Post Catalog | Post Catalog | Post Catalog | Post Catalog | Post Catalog
Published posts parsed from src/content/posts.ts for later data-driven route, feed, and sitemap tests. | Published posts parsed from src/content/posts.ts for later data-driven route, feed, and sitemap tests. | Published posts parsed from src/content/posts.ts for later data-driven route, feed, and sitemap tests. | Published posts parsed from src/content/posts.ts for later data-driven route, feed, and sitemap tests. | Published posts parsed from src/content/posts.ts for later data-driven route, feed, and sitemap tests. | Published posts parsed from src/content/posts.ts for later data-driven route, feed, and sitemap tests.
Slug | Title | Date | Tags | Social Image | Description
make-yourself-obsolete | Make Yourself Obsolete | 2026-06-11 | career, engineering, automation, growth | Yes | A practical career note on turning repeated work into automation, documentation, and room for harder problems.
intune-gotchas-every-admin-learns-eventually | Intune Gotchas Every Admin Learns Eventually | 2026-06-10 | intune, endpoint-management, windows, security, device-management | Yes | The Microsoft Intune behaviors that surprise admins most often, why they happen, and how to avoid getting burned by them.
intune-hydration-kit-has-a-tui-now | Intune Hydration Kit Has a TUI Now | 2026-06-01 | powershell, intune, automation, microsoft-graph, endpoint-management | Yes | The v1.0.0 update makes Invoke-IntuneHydration safer to run by putting dry-run, scope, platform, and confirmation prompts in the default path.
mmsmoa-2026-endpoint-management-is-engineering-now | MMSMOA 2026: Endpoint Management Is an Engineering Discipline Now | 2026-05-30 | intune, endpoint-management, powershell, automation, windows, security, conference | Yes | A practical MMSMOA recap for Intune, Windows, security, PowerShell, and automation work that needs to survive real operations.
reusable-intune-remediation-template | Build a Reusable Intune Remediation Template | 2026-05-25 | powershell, intune, remediations, windows, scripting | Yes | A reusable PowerShell pattern for Intune Remediations with predictable exit codes, logging, 64-bit handling, and portal-friendly output.
creating-dynamic-device-model-groups-in-entra-with-powershell | Creating Dynamic Device Model Groups in Entra with PowerShell | 2026-05-12 | powershell, intune, entra-id, microsoft-graph, automation | Yes | A PowerShell walkthrough for creating OS-scoped dynamic Entra device groups based on Intune device models.
set-up-and-view-app-inventory-data-in-intune | Set Up and View App Inventory Data in Intune | 2026-05-07 | intune, windows, device-management, application-inventory, tutorial | No | App inventory gives you richer Windows app data in Intune, but only after you turn it on with a Properties catalog policy.
ai-agents-changed-how-i-build-things | AI Coding Agents Changed How I Build Things | 2026-05-05 | llm, ai, powershell, automation, github-copilot | No | I used to think LLMs were just fancy autocomplete. Then I started letting them live inside my repos. Here's what changed.
hello-world | Hello, World | 2026-05-01 |  | No | Welcome to my new blog. Built with React, Vite, and MDX.
powershell-summit-2026-we-are-all-insane-and-that-is-the-opportunity | PowerShell Summit 2026: We Are All Insane, and That Is the Opportunity | 2026-04-18 | powershell, ai, automation, career, conference | No | To quote Jeffrey Snover, "you are all insane." Not as an insult. As a diagnosis.
using-net-methods-in-powershell-with-practical-examples-youll-actually-reuse | Using .NET Methods in PowerShell (with practical examples you'll actually reuse) | 2026-02-14 | powershell, dotnet, scripting, tutorial | No | PowerShell is already sitting on top of .NET. Here are the patterns I use most: strings, paths, file I/O, time, crypto, and more.
bootstrap-your-intune-tenant-in-a-single-command | Bootstrap Your Intune Tenant in a Single Command | 2025-12-28 | powershell, intune, automation, microsoft-graph, devops | No | Turn a fresh Intune tenant into a best-practice baseline without babysitting the portal using the Intune Hydration Kit PowerShell module.
finding-wmi-usage-before-microsoft-finds-it-for-you | Finding WMI Usage Before Microsoft Finds It For You | 2025-10-12 | powershell, wmi, cim, windows, scripting | No | Microsoft is deprecating WMIC and legacy WMI cmdlets. Find every instance in your codebase before your scripts start breaking in production.
winget-without-winget-building-a-cross-platform-package-manifest-fetcher | WinGet Without WinGet: Building a Cross-Platform Package Manifest Fetcher | 2025-07-20 | powershell, winget, cross-platform, github-api, devops | No | Query WinGet packages from macOS or Linux by hitting the winget-pkgs GitHub repo directly - no WinGet client required.
supercharge-microsoft-graph-api-data-retrieval-with-powershell-batch-requests | Supercharge Microsoft Graph API Data Retrieval with PowerShell Batch Requests | 2025-07-15 | powershell, microsoft-graph, performance, api, automation | No | Reduce Graph API data export times by up to 88% using batch requests and parallel processing. Real production metrics included.
are-you-even-good-enough-to-have-imposter-syndrome | Are You Even Good Enough to Have Imposter Syndrome? | 2025-04-18 | career, growth, mental-health, engineering | No | Imposter syndrome doesn't go away. If anything, it scales with you. Here's how to use it as fuel rather than fear.
back-up-or-restore-jamf-pro-objects-with-powershell | Back Up or Restore Jamf Pro Objects with PowerShell | 2025-03-23 | powershell, jamf, mdm, backup, automation | No | A PowerShell tool for backing up and restoring Jamf Pro configurations with selective exports, OAuth support, and organized backups.
synchronizing-device-groups-with-entra-user-groups-using-powershell | Synchronizing Device Groups with Entra User Groups Using PowerShell | 2025-02-03 | powershell, intune, entra-id, microsoft-graph, automation | No | Given a list of usernames, automatically find their Intune-managed devices and sync them to a device group using parallel Graph API calls.
syncing-abm-and-vpp-tokens-with-intune-a-powershell-script-for-the-lazy-admin | Syncing ABM and VPP Tokens with Intune: A PowerShell Script for the Lazy Admin | 2024-08-31 | powershell, intune, apple, abm, automation | No | Automate the manual process of syncing Apple Business Manager and Volume Purchase Program tokens in Microsoft Intune with PowerShell.
automating-device-management-with-powershell-function-invoke-appinstalleddevicesgroup | Automating Device Management with PowerShell: Function Invoke-AppInstalledDevicesGroup | 2024-03-03 | powershell, intune, automation, microsoft-graph, scripting | No | Build a device group in Intune based on detected application installs - automatically add and remove devices as software appears and disappears.
intune-device-queries-to-level-up-your-device-management | 20+ Intune Device Queries to Level Up Your Device Management | 2024-02-19 | intune, kql, device-management, windows, microsoft | No | Leverage Kusto Query Language with Intune Device Query to gain deep insights into your device fleet, from BIOS info to installed applications.
streamlining-application-detection-in-intune-and-mecm-with-powershell | Streamlining Application Detection in Intune and MECM with PowerShell | 2024-01-05 | powershell, intune, mecm, application-detection, scripting | No | A PowerShell function for precise application detection across 32-bit, 64-bit, and user-context installs - perfect for Intune Win32 app detection.
top-20-graph-api-cmdlets | Top 20 Graph API Cmdlets | 2023-07-31 | powershell, microsoft-graph, microsoft-365, automation, tutorial | No | A practical tour of the 20 most useful Microsoft Graph PowerShell cmdlets for managing users, groups, devices, apps, and more in Microsoft 365.
using-filters-to-assign-apps-policies-and-profiles-in-microsoft-intune | Using Filters to Assign Apps, Policies, and Profiles in Microsoft Intune | 2023-05-14 | intune, device-management, microsoft, tutorial | No | A comprehensive guide to using Intune device filters to dynamically target devices based on properties like manufacturer, model, and OS version.
proactive-remediation-to-remind-windows-users-to-reboot | Proactive Remediation to Remind Windows Users to Reboot | 2023-05-07 | intune, powershell, proactive-remediation, windows | No | Use Intune Proactive Remediations to detect Windows devices that haven't rebooted in 7+ days and display a customizable toast notification reminder.
find-registry-uninstall-keys-with-powershell | Find Registry Uninstall Keys with PowerShell | 2023-05-07 | powershell, windows, registry, scripting, uninstall | No | A PowerShell function to search the Windows registry for uninstall keys matching a specified string, with support for 64-bit and 32-bit applications.

## Project Catalog
Project Catalog | Project Catalog | Project Catalog | Project Catalog | Project Catalog | Project Catalog | Project Catalog
Project cards parsed from src/pages/Projects.tsx for later link, card-count, and CTA tests. | Project cards parsed from src/pages/Projects.tsx for later link, card-count, and CTA tests. | Project cards parsed from src/pages/Projects.tsx for later link, card-count, and CTA tests. | Project cards parsed from src/pages/Projects.tsx for later link, card-count, and CTA tests. | Project cards parsed from src/pages/Projects.tsx for later link, card-count, and CTA tests. | Project cards parsed from src/pages/Projects.tsx for later link, card-count, and CTA tests. | Project cards parsed from src/pages/Projects.tsx for later link, card-count, and CTA tests.
Section | Name | Kind | Href | CTA | Tags | Description
Live projects | Intune Hydration Kit | Product | https://www.intunehydrationkit.com/ | Visit site | Intune, Graph, Automation | Bootstrap Microsoft Intune tenants with baseline policies, compliance, Conditional Access, Microsoft Graph deployment, previews, and safety checks.
Live projects | Endpoint Jobs | Job board | https://endpointjobs.dev/ | Visit site | Endpoint, Careers, MDM | Focused job board for endpoint engineering, MDM, UEM, client platform, and endpoint security roles.
Live projects | Graph Explorer Plus | Graph app | https://graphexplorerpl.us/ | Visit site | TypeScript, Graph, Next.js | Power-user Microsoft Graph explorer with curated samples, resource browsing, code snippets, and sovereign cloud support.
Live projects | Tenant Graph | Tenant map | https://tenantgraph.com/ | Visit site | Intune, Entra, Graph | Visualizes Microsoft Intune and Entra relationships across users, devices, groups, apps, policies, and Conditional Access.
Live projects | NukeTune | Tenant reset | https://nuketune.com/ | Visit site | TypeScript, Intune, Graph | Bulk deletion tool for resetting Intune environments across devices, apps, policies, and configurations.
Live projects | Intune Gazette | Docs tracker | https://jorgeasaurus.github.io/IntuneDocsAutomation/ | Visit site | Intune, Docs, GitHub Actions | Static newspaper-style dashboard that tracks Microsoft Intune documentation updates from Microsoft Learn.
Repos and experiments | InTUI | Terminal UI | https://github.com/jorgeasaurus/InTUI | View repository | PowerShell, Intune, TUI | PowerShell terminal interface for managing Microsoft Intune through Microsoft Graph.
Repos and experiments | Win32Forge | Packaging | https://jorgeasaurus.github.io/Win32Forge/ | Visit site | PowerShell, Intune, Win32 | Package, publish, and deploy Intune Win32 apps with repeatable metadata and Graph upload workflows.
Repos and experiments | MgGraphIndex | Reference | https://jorgeasaurus.github.io/MgGraphIndex/ | Visit site | Graph, PowerShell, Reference | Searchable static index for Microsoft Graph PowerShell cmdlets, refreshed by GitHub Actions.
Repos and experiments | PSModuleBrowser | Terminal UI | https://github.com/jorgeasaurus/PSModuleBrowser | View repository | PowerShell, Gallery, TUI | Keyboard-driven terminal interface for searching, inspecting, and installing PowerShell Gallery modules.
Repos and experiments | WinGet-Manifest-Fetcher | Module | https://github.com/jorgeasaurus/WinGet-Manifest-Fetcher | View repository | PowerShell, WinGet, Packaging | PowerShell module for reading installer details from WinGet manifests without requiring the WinGet client.
Repos and experiments | FleetDM-PowerShell | API wrapper | https://github.com/jorgeasaurus/FleetDM-PowerShell | View repository | PowerShell, FleetDM, API | PowerShell wrapper module for the FleetDM API.
Repos and experiments | WinStoreRip | CLI | https://github.com/jorgeasaurus/WinStoreRip | View repository | PowerShell, Windows Store, CLI | Command-line tool for querying and downloading Windows Store app packages.
Repos and experiments | PSRedditTUI | Terminal UI | https://github.com/jorgeasaurus/PSRedditTUI | View repository | PowerShell, Reddit, TUI | PowerShell terminal interface for browsing Reddit, favorites, and subreddit data through JSON endpoints.
Repos and experiments | JamfAssignmentChecker | Audit tool | https://github.com/jorgeasaurus/JamfAssignmentChecker | View repository | PowerShell, Jamf, Audit | Checks Jamf Pro assignments across computers, users, and groups.
Repos and experiments | Intune-Snapshot-Recovery | Recovery | https://github.com/jorgeasaurus/Intune-Snapshot-Recovery | View repository | PowerShell, Intune, Backup | PowerShell and GitHub Actions toolkit for backing up and restoring Intune tenant configuration.
Repos and experiments | PsJamfBackupRestore | Recovery | https://github.com/jorgeasaurus/PsJamfBackupRestore | View repository | PowerShell, Jamf, Backup | PowerShell utility for backing up and restoring Jamf Pro configuration through the Jamf API.
Repos and experiments | MgConsoleGuiGraphSearch | Console GUI | https://github.com/jorgeasaurus/MgConsoleGuiGraphSearch | View repository | PowerShell, Graph, Console | Console GUI search for Microsoft Graph objects across Microsoft 365 and Entra.
Repos and experiments | PSIntuneWinDetection | Generator | https://github.com/jorgeasaurus/PSIntuneWinDetection | View repository | PowerShell, Intune, Detection | Reusable generator for PowerShell detection scripts used by Windows app deployments.
Repos and experiments | PS-MDR | Game | https://github.com/jorgeasaurus/PS-MDR | View repository | PowerShell, Game, Console | Console-based interactive game implemented in PowerShell around macro data refinement.